## Calendar
UW Academy Month-end Close Calendar Fiscal Year End 2025
Calendar for June 2025 will be a 18 business day process.
Note: Last day of the calendar month is called "Day minus 1". Day 1 -18 are business days.
Last updated April 11, 2025
WD Period | Month | Date | Day of Close | Deadline | Key Functions and types of transactions that occur each day
July | June | 30 | Day minus 1 | midnight | Open July ledger period in Workday
June | June | 30 | Day minus 1 | 14:00 | Last day to approve Accounting Adjustments for period (follows Procurement close)
June | June | 30 | Day minus 1 | midnight | Complete receiving of goods and services for period
June | June | 30 | Day minus 1 | midnight | Close Procurement, Expenses, Capital Assets, Student Accounts
June | June | 30 | Day minus 1 | midnight | Last day to post ISDs (follows Procurement close)
June | July | 1 | Day 1 | midnight | Close Banking
June | July | 1 | Day 1 | 14:00 | In-progress customer invoices must be approved or cancelled (if not approved) by 2pm
June | July | 1 | Day 1 | 17:00 | Close Customer Accounts
June | July | 1 | Day 1 | 17:00 | Run Receipt Accrual
June | July | 2 | Day 2 | 17:00 | Run Depreciation
June | July | 2 | Day 2 | 17:00 | Post reversing journal
June | July | 3 | Day 3 | -
June | July | 4 | - | - | Holiday
June | July | 5 -6 | - | - | Weekend
June | July | 7 | Day 4 | midnight | Payroll posts; Time of day is dependent upon Payroll processes completing and may be earlier/later than midnight.
June | July | 8 | Day 5 | -
June | July | 9 | Day 6 | -
June | July | 10 | Day 7 | -
June | July | 11 | Day 8 | 17:00 | Surveys due to Controller's Office: Accounts Receivable, Unearned Revenue and Inventory
June | July | 12-13 | - | - | Weekend
June | July | 14 | Day 9 | - | Courtesy Dean's Day - If posting to another Balancing Unit (BU), communicate in advance
June | July | 14 | Day 9 | 17:00 | Close Payroll; Fringe expenses post. All Payroll Accounting Adjustments (PAA) must be approved to be captured in June.
June | July | 15 | Day 10 | 12:00 | Funding Source - final task run for period
June | July | 15 | Day 10 | 14:00 | Last day to run financial allocations - 2pm cut-off
June | July | 15 | Day 10 | 14:00 | In-progress journals must be approved or cancelled (if not approved) by 2pm
June | July | 15 | Day 10 | 17:00 | Close Journals (except for Controller's Office)
June | July | 15 | Day 10 | 17:00 | Close Operational Accounting
June | July | 16 | Day 11 | - | Controller's Office Only
June | July | 17 | Day 12 | - | Controller's Office Only
June | July | 18 | Day 13 | - | Controller's Office Only
June | July | 19-20 | - | - | Weekend
June | July | 21 | Day 14 | - | Controller's Office Only
June | July | 22 | Day 15 | - | Controller's Office Only
June | July | 23 | Day 16 | - | Controller's Office Only ~ UCO final review WD companies close: UWMC, ALNW, UWMSS, SOM, MT, PBI, WBRP
June | July | 24 | Day 17 | - | Controller's Office Only ~ UCO final review
June | July | 25 | Day 18 | 17:00 | University closes Workday for fiscal year ~ rollforward to fiscal year 2026
June | July | 28-31 |  |  | Submit & post trial balance to State Agency Financial Reporting System (AFRS)
~ University in Post Close Period until audited financial statements issued ~

## 1. YE Calendar (hidden)
UW Enterprise Close Calendar - Fiscal Year End 2024 |  |  |  |  | DRAFT - 3.12.24
In Process
Calendar Date | Calendar Day | Day of Close | Deadline | Key Function | Dependencies?
2024-06-25 | Tuesday | -5 |  | Initiate June Close
2024-06-26 | Wednesday | -4
2024-06-27 | Thursday | -3
2024-06-28 | Friday | -2
2024-06-29 | Saturday | weekend
2024-06-30 | Sunday | -1 | 14:00 | Last day to approve Accounting Adjustments for period (follows Procurement close) | Calendar date dependent
2024-06-30 | Sunday | -1 | midnight | Complete receiving of goods and services for period | Calendar date dependent
2024-06-30 | Sunday | -1 | midnight | Close Procurement, Expenses, Capital Assets, Student Accounts | Action Item: Confirm all WD modules are Calendar date dependent
2024-06-30 | Sunday | -1 | midnight | Last day to post ISDs (follows Procurement close) | Part of Procurement- Calendar date dependent
2024-07-01 | Monday | 1 | midnight | Close Banking | Calendar date dependent
2024-07-01 | Monday | 1 | 14:00 | In-progress customer invoices must be approved or cancelled (if not approved) by 2pm | Calendar date dependent
2024-07-01 | Monday | 1 | 17:00 | Close Customer Accounts | Calendar date dependent
2024-07-01 | Monday | 1 | 17:00 | Run Receipt Accrual | Part of Procurement- Calendar date dependent
2024-07-02 | Tuesday | 2 | 17:00 | Run Depreciation
2024-07-02 | Tuesday | 2 | 17:00 | Post reversing journal
2024-07-03 | Wednesday | 3
2024-07-04 | Thursday | Holiday
2024-07-05 | Friday | 4 | midnight | Close Payroll; Fringe expenses post. Time of day is dependent upon Payroll processes completing and may be earlier/later than midnight.
2024-07-06 | Saturday | weekend
2024-07-07 | Sunday | weekend
2024-07-08 | Monday | 5 | -
2024-07-09 | Tuesday | 6 | -
2024-07-10 | Wednesday | 7 | - | GCA bills grants on Day 7 | Transactions with grant worktags; Action Item: What flexibility if any there is with grant billing?
2024-07-11 | Thursday | 8 | -
2024-07-12 | Friday | 9 | 14:00 | In-progress journals must be approved or cancelled (if not approved) by 2pm
2024-07-12 | Friday | 9 | 14:00 | Last day to run financial allocations - 2pm cut-off | Action Item: List out all dependencies per allocation
2024-07-12 | Friday | 9 | 17:00 | Close Operational Accounting
2024-07-12 | Friday | 9 | 17:00 | Close Journals (except for Controller's Office)
2024-07-13 | Saturday | weekend
2024-07-14 | Sunday | weekend
2024-07-15 | Monday | 10 | - | Controller's Office Only
2024-07-15 | Monday | 10 |  | AFRS Closes for June 2024 | Need to ensure May is posted to AFRS
2024-07-16 | Tuesday | 11 | - | Controller's Office Only
2024-07-17 | Wednesday | 12 |  | Controller's Office Only
2024-07-18 | Thursday | 13 |  | Controller's Office Only
2024-07-19 | Friday | 14 |  | Controller's Office Only
2024-07-20 | Saturday | weekend
2024-07-21 | Sunday | weekend
2024-07-22 | Monday | 15 |  | Controller's Office Only
2024-07-23 | Tuesday | 16 | 17:00 | University Final Close and Consolidated Financial Reporting
2024-07-23 | Tuesday | 16 |  | Latest day UW can close WD to meet AFRS system close requirements for phase I | Batch processing for file sent to State. Needs overnight to process for EDW
2024-07-24 | Wednesday | 17 |  | Submit trial balance to State Agency Financial Reporting System (AFRS) | Batch processing for file. Error remediation starts next day
2024-07-25 | Thursday | 18 |  | AFRS error remediation
2024-07-26 | Friday | 19 |  | AFRS error remediation
2024-07-27 | Saturday | weekend
2024-07-28 | Sunday | weekend
2024-07-29 | Monday | 20 |  | AFRS error remediation
2024-07-30 | Tuesday | 21 |  | AFRS error remediation
2024-07-31 | Wednesday | 22 |  | AFRS Phase I closes
July Close |  |  |  | Prep allocations
Post Close Phase
2024-07-29 | Monday |  |  | Trial balance to KPMG - UW1861, SOM, MT, UWMC, ALNW, UWMSS; Component Units: PBI
2024-07-29 | Monday |  |  | Trial balance to KPMG - Fiduciary
2024-09-23 | Monday |  |  | Trial balance to KPMG - Component Units: WBRPs, UWP, UWMPC (former MJV N.16)
2024-08-30 | Friday |  |  | Post Close Entries - Round 1
2024-09-23 | Monday |  |  | Post Close Entries - Round 2 | Pension; OPEB; WBRP trial balance
2024-09-30 | Monday |  |  | Post Close Entries - Round 3 | MV adjustment
2024-10-11 | Friday |  |  | Post Close Entries - Round 4 Final (after Controller's Office finishes analytic for Enterprise)
2024-10-18 | Friday |  |  | Finalize UW trial balance in AFRS - UW and Component Units
Reporting Phase - Issuance dates
2024-10-18 | Friday |  |  | UW Medicine Select Units financial statements issued
2024-11-01 | Friday |  |  | UW issues FY24 Enterprise Financial Statements
2024-11-01 | Friday |  |  | UW issues FY24 GRB
2024-11-01 | Friday |  |  | UW Housing & Food Services (HFS)
2024-11-01 | Friday |  |  | Intercollegiate Athletics (ICA)
2024-11-01 | Friday |  |  | Internal Lending Program (ILP)
What are FY24 dates for these reports?
|  |  | 2023-09-20 | Metropolitan Tract
|  |  | 2023-10-10 | Portage Bay Insurance (PBI)
|  |  | 2023-09-21 | Washington Biomedical Research (WBRPs) x4
|  |  | 2023-09-25 | Valley Medical Center (VMC)
|  |  | 2023-10-13 | UW Medicine Select Units
|  |  | 2023-10-13 | Fred Hutchinson Cancer Center (FHCC)
|  |  | 2023-10-13 | Harborview Medical Center (HMC)
|  |  | 2023-11-09 | UW Foundation
|  |  | 2023-11-02 | UW Alumni

## 1. Task list (hidden)
List of Open Items to address and schedule in YE Calendar
Business Unit | Items to Address | Contacts | Notes | Dependencies? | Status
Financial Accounting | Deans Day? FY23 occurred on July 14th or day 9 |  | What is equivalent for FY24?
Financial Accounting | Review FR YE Task List and impact to Close & Post Close Phase | Susan Stolle
Financial Accounting | Establish Financial Reporting YE JE list | Yi Guo & Susan Stolle
Financial Accounting | Draft list out known late entries - ie pension, MV to better inform dates to post | Susan Stolle / Yi Guo
Financial Accounting | AR Survey Accrual
Financial Accounting | Unearned Revenues
Financial Accounting | Customer Accounts: AR, Unearned, Revenue
Financial Accounting | Appropriation revenue/AR
Financial Accounting | Inventory Survey
Financial Accounting | Project 4311 (Welcome Center) - pending new WD Company
Financial Accounting | Consolidation & Elimination process
Financial Accounting | Completeness - integregations
Financial Accounting | GLARP - GL Account Reconciliation Process | Alisha Jiwa
Financial Accounting | Dust off the fiscal period close process and refresh
Financial Accounting | Develop business process for post close phase
Financial Accounting | Impact to Allocations if close is extended | Yi Guo & Various
Financial Accounting | Controller's Checklist | Erick Winger / Susan Stolle | Needs to be reviewed and updated for WD processes ; Determine timeline for FY24 process
Financial Accounting | ICFR narrative | Erick Winger
Financial Accounting | Audit Report - Issuance dates |  | Timing of CU -WBRPS, UWP, UWMPC, PBI Auxiliary Units: HFS, MT, ICA, Medicine Related Parties: UWAA, UWF, HMC
Financial Accounting | Define usage of WD Book codes: GASB & YE
Equipment Inventory Office (EIO) | Asset capitalization and depreciation | Erik Benningson
Customer Accounts - AR, Unearneds, Revenue |  | See Jason or Erick for contact
GCA | Grants: Billing | Julie Fricks/Kirsten
ICA |  | Julia Ramos
Medicine | Coordination with Medicine WD companies | Lisa Pascuzzi
Office of Financial Management (OFM) | State Reporting: Coordinate w/ AFRS YE close dates | Susan Stolle / Anna Quichocho
Payroll | Payroll; Payroll suspense acct clean up | Ginny Montegomery/Shawna Litterski
Portage Bay Insuracne (PBI) | PBI | Tim Gault
Project Delivery Group (PDG) | CIP Accrual | Chiaka Amadi
Procurement - AP | AP accrual (AP Triangle) in coordination with Receipt Accrual process | Pramela
Procurement -Procard | Procard accrual | Arnold | 4/8-Will need a June accrual for expenses not approved and posted to June but paid in July
Procurement -Travel/Customer Svc |  | Teresa
Procurement - Tax Office | Tax accruals
Procurement - Facilities | Other Procurement integrations - Facilities | Andrew Fenzel
Procurement - HFS | Other Procurement integrations - HFS | Ha Tran/ Socrates Red
Procurement - Law Library | Other Procurement integrations - Law Library | Andrea Arrington/ Perarl McCrea
Procurement - Libraries | Other Procurement integrations - Libraries | Kathleen Larson; Ian Dotson
Procurment - Real Estate | Other Procurement integrations - Real Estate/ Yardi | Arlene Hoehnen
Real Estate | Metro Tract | Greg Miller/Arlene Hoehnen
Shared Environment
SOM | Sshool of Medicine (SOM) | Christine Ward
Treasury | Cash & Banking | Mark Park
Treasury | Treasury - Debt | Omar Johnson/Robert Bradshaw
Treasury | Treasury -Investments | Leilani Marquez/ Robert Bradshaw
UW Alumni Association (UWAA)
UW Foundation (UWF)
Communications | Communication - update FR website
Communications | Communication - Email distribution
Communications | Communication - instructions/job aids
Communications | Accounting Forum |  | Target: May 14th ; June 11th
Communications | Shared Environnment |  | Occurs weekly - need to choose target date(s)
Communications | Procurement Office Hours |  | Occurs every two weeks - need to choose target date(s)
integrations in by end of month? | Jackson Lum; Paul H Prestinand folks; SWIFT program
Integrations | Jennifer Loveridge