## Slide 1
F&A Rate Proposal Project Update
MRAM
January 12, 2023
Colleen Bettis, Director MAA
Sponsored Programs Finance
UW Finance

## Slide 2
Agenda
Project Update
  Year in Review
  Space Inventory
  Financials Validation
Timeline
Next Steps
  Training
  Space Survey
Questions

## Slide 3
Project Update
Outcomes
  Reconciled to financial statements
  Updated cost pool algorithm
  Developed SQL code for base year data
  Established space survey threshold
Lessons Learned
  Revised data mapping since FY13
  Refined inventory processes: InVision/WebSpace
Practice Year in Review

## Slide 4
Project Update
8-week initiative, concluded 11/30
InVision vs. WebSpace
Partnership with Facilities
Base Year: Space Inventory - Complete

## Slide 5
Project Update
Participation
  70 departments from 11 Schools/Colleges
  124 system users
Room Updates
  9,736 rooms, or 11% of all UW space was updated
  951 previously unclassified rooms were assigned primary use
Assignable Square Feet
  221,500 additional square feet identified as research space
  Represents 10% increase
Base Year: Space Inventory - Outcomes

## Slide 6
Project Update
Cost Pools
  990 assigned since OCT
  709 budgets assigned during practice year
Refining Practice Year Model
  Refining cost pools
  Updating allocation methods for costs
Base Year: Financials Validation

## Slide 7
Timeline

## Slide 8
Next Steps
WebSpace Training
  Inventory Training
    Early January 2023
  Survey Training
    Late January 2023
Survey
  Completed in Webspace
    Feb-April 2023
Space Survey

## Slide 9
Questions?
Thank you for your time!
fahelp@uw.edu